Allied Systems Integrations

PROJECT PROPOSAL

Version 1.0

Cloud-Based Access Control System Upgrade

Keri Borealis + Connekt Mobile Credentials | 10-Door Clubhouse Configuration

PREPARED FOR

Diamond Heights Village Association

c/o PMP Management, LLC

Attn: Melissa Tolerton

115 Red Rock Way, San Francisco, CA 94131

March 18, 2026

## Confidentiality Notice

This document contains proprietary and confidential information belonging to ASI 360 (Allied Systems Integrations). The information provided herein is intended solely for the use of Diamond Heights Village Association and its authorized representatives. Distribution, reproduction, or disclosure of this document or its contents to any third party without the prior written consent of ASI 360 is strictly prohibited.

All pricing, technical specifications, and methodologies described herein are valid for thirty (30) days from the date of this proposal unless otherwise stated.

# Cover Letter

March 18, 2026

Diamond Heights Village Association

c/o PMP Management, LLC

Attn: Melissa Tolerton

115 Red Rock Way

San Francisco, CA 94131

Dear Ms. Tolerton,

Thank you for the opportunity to assess the access control system at Diamond Heights Village. Following our detailed evaluation of your existing Keri Systems PXL-500 infrastructure, we are pleased to present this proposal for a comprehensive system upgrade that will modernize your security while protecting your existing investment in wiring and controllers.

This proposal includes a complete needs assessment based on our on-site evaluation, a detailed technical solution design, an itemized investment summary, and our recommended implementation timeline. We have designed this solution to address the specific challenges faced by your community, including aging readers, the need for modern credential management, and enhanced security for common areas.

We look forward to discussing this proposal with you and the Board of Directors. Please do not hesitate to contact us with any questions.

Sincerely,

ASI 360 — Allied Systems Integrations

San Francisco Bay Area

info@asi360.co | (510) 288-0994

# Executive Summary

Diamond Heights Village Association operates a Keri Systems PXL-500-based access control system controlling 10 doors across the residential complex. The system uses legacy NXT/MS-series proximity readers with a PXL-250 Tiger Controller as the head-end. While the core infrastructure remains functional, the readers are aging, the Tiger controller lacks cloud management capability, and the community has no modern credential options.

ASI 360 proposes upgrading to the Keri Borealis cloud-based platform with Farpointe Conekt mobile smartcard readers (CSR-35L). This approach replaces the Tiger controller and all 10 readers while retaining the existing PXL-500 controllers, wiring, power supply, and enclosures — protecting the Association’s existing investment.

Hardware Investment: $16,696.75 (incl. tax)

Services Investment: $6,300.00

Combined Total: $22,996.75

Estimated Timeline: 4-5 weeks from signed acceptance

Payment Terms: 50% deposit / 40% on install / 10% on commissioning

# Needs Assessment

Based on our comprehensive assessment of the Diamond Heights Village access control system, we identified the following conditions and risk factors that drive the need for a system upgrade.

## Current System Conditions

- 10-door access control system with 10 proximity readers across residential HOA complex

- 4x Keri PXL-500 controllers (2018-2019 manufacture) in KRE-2 enclosures — functional, good condition

- 1x PXL-250 Tiger Controller serving as head-end — functional but legacy technology, no cloud capability

- 8x MS-5000 series mullion readers — fair condition, significant weathering from outdoor exposure

- 2x NXT-2R/3R mid-size readers — poor condition, severe UV degradation, priority replacement

- KPS-11 power supply with ESD X-1656 transformer — good condition, compatible with upgrade

- 2x Interstate FAS1075 backup batteries (12V 7Ah) — age unknown, on-site testing recommended

- All readers use legacy 26-bit Wiegand NXT/MS proximity technology

- Existing wiring infrastructure (Wiegand runs, power, RS-485 bus) is intact and reusable

## Risk Factors

- Tiger PXL-250 controller has no cloud management — all changes require on-site visits

- Legacy proximity-only readers provide no mobile credential or PIN code capability

- UV-degraded readers (Readers 2 and 3) are at risk of failure

- No audit trail capability — cannot track who accessed what door and when

- Credential management requires physical office visits to issue/revoke fobs

- No temporary or guest credential capability for contractors and visitors

- Pool and common area access lacks granular time-based scheduling

- Competitor quote (Warman Security) is active — 30-day expiration window

- Aging backup batteries may not sustain system during power outages

# Proposed Solution

ASI 360 recommends a Keri Borealis cloud migration with Farpointe Conekt CSR-35L mobile smartcard readers, providing Diamond Heights Village with a modern, smartphone-first access control experience.

## System Components

- Keri Borealis Cloud Hub (KB-HUB) — Cloud controller replacing the legacy Tiger PXL-250. Provides remote management, real-time monitoring, and cloud-based credential administration from any browser.

- 10x Farpointe Conekt CSR-35L Mobile Smartcard Readers (Mullion) — Replace all existing MS-5000 and NXT-2R/3R readers. Support both traditional proximity fobs and Conekt Bluetooth mobile credentials. No keypad.

- 700 Conekt Mobile Phone Credentials (CMC-2) — Residents receive credentials via email and activate on their smartphones. No office visit required for provisioning.

- 200 Conekt Proximity Key Tags (4x CSK-2-50 packs) — For residents who prefer physical credentials or do not have compatible smartphones.

- Borealis 10-Door Cloud Subscription (BOREALIS-1D-MO) — Cloud hosting, firmware updates, and remote management platform. $19.95/door/month.

- 2x Replacement Backup Batteries (12V 7Ah SLA) — Ensures reliable power backup.

## Retained Equipment

- 4x PXL-500 controllers (Borealis Hub communicates via RS-485)

- 5x KRE-2 enclosures

- KPS-11 power supply

- ESD X-1656 transformer

- All existing wiring (Wiegand runs, power, RS-485 bus)

# Key Benefits

- Mobile-first credentials — no office visits, instant provisioning via email

- Temporary/guest codes with auto-expiry for contractors and visitors

- Remote credential management from anywhere via Borealis cloud dashboard

- Complete audit trail for compliance and liability protection

- Pool safety — controlled access prevents unauthorized entry (liability reduction)

- Package theft prevention — secured mail/package room access

- Instant move-out revocation — no chasing physical fobs

- Scalable to full 60-door campus (Phase 2) without replacing any equipment

# Investment Summary

## Hardware & Equipment

| # | Item (SKU) | Description | Qty | Unit Price | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | KB-HUB | Keri Borealis Cloud Hub Controller | 1 | $574.00 | $574.00 |
| 2 | CSR-35L | Farpointe Conekt Mobile Smartcard Reader (Mullion) | 10 | $325.00 | $3,250.00 |
| 3 | CMC-2 | Conekt Mobile Phone Credential (annual license) | 700 | $10.00 | $7,000.00 |
| 4 | CSK-2-50 | Conekt Proximity Key Tags (50-pack) | 4 | $520.00 | $2,080.00 |
| 5 | BOREALIS-1D-MO | Borealis Cloud Subscription (10 doors × 12 months) | 1 | $2,394.00 | $2,394.00 |
| 6 | 12V-7AH-SLA | Backup Battery (12V 7Ah Sealed Lead Acid) | 2 | $36.50 | $73.00 |
|  |  | Hardware Subtotal |  |  | $15,371.00 |
|  |  | CA Sales Tax (8.625%) |  |  | $1,325.75 |
|  |  | Hardware Total |  |  | $16,696.75 |

## Services & Installation

| # | Item | Description | Qty | Unit Price | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | INSTALL-READER | Reader removal, mounting, wiring, termination | 10 | $185.00 | $1,850.00 |
| 2 | INSTALL-HUB | Borealis Hub install, network config, commissioning | 1 | $750.00 | $750.00 |
| 3 | PROGRAM | System programming, credential enrollment, testing | 1 | $1,200.00 | $1,200.00 |
| 4 | CONNEKT-SETUP | Connekt mobile platform setup, templates, onboarding | 1 | $950.00 | $950.00 |
| 5 | TRAINING | Property management staff training (2 sessions) | 1 | $500.00 | $500.00 |
| 6 | PM | Project management, coordination, documentation | 1 | $800.00 | $800.00 |
| 7 | DISPOSAL | Legacy Tiger controller + old reader disposal | 1 | $250.00 | $250.00 |
|  |  | Services Total |  |  | $6,300.00 |

## Combined Investment

Hardware Total (incl. tax): $16,696.75

Services Total: $6,300.00

Combined Project Total: $22,996.75

# Terms & Conditions

## Payment Terms

- 50% deposit upon signed acceptance to initiate equipment procurement

- 40% upon completion of hardware installation

- 10% upon system commissioning, testing, and client sign-off

## Warranty

- All labor warranted for one (1) year from date of commissioning

- Manufacturer hardware warranties apply per Keri Systems and Farpointe standard terms

- Borealis cloud subscription is billed annually and subject to Keri Systems subscription terms

## Scope Exclusions

- Electrical work beyond low-voltage access control wiring

- Door hardware modifications, lock replacements, or gate operator repairs

- Network infrastructure (Ethernet drops, switches, routers, ISP coordination)

- Painting, patching, or cosmetic repairs following reader replacement

- Wiring repairs discovered during installation will be quoted separately on a T&M basis

## Timeline

- Equipment lead time: 2-3 weeks from deposit

- Installation: 2-3 business days

- Commissioning and training: 1 business day

- Estimated project completion: 4-5 weeks from signed acceptance

## Validity

This proposal is valid for thirty (30) days from the date shown on the cover page. Pricing is subject to change after the validity period due to manufacturer price adjustments and equipment availability.

# Acceptance

By signing below, the authorized representative of Diamond Heights Village Association accepts this proposal and authorizes ASI 360 to proceed with the project as described herein.

________________________________________          ________________

Authorized Signature                                                        Date

________________________________________

Printed Name & Title

ASI 360 — Allied Systems Integrations

San Francisco Bay Area | info@asi360.co | (510) 288-0994

# Comparison at a Glance

The following table summarizes all three proposal options side by side to assist the Board of Directors in evaluating the best fit for Diamond Heights Village.

| Feature | V1 Borealis Mobile | V2 Hybrid Keypad | V3 NXT Standard |
| --- | --- | --- | --- |
| Entry Methods | Fob + Mobile | PIN + Fob + Mobile | PIN + Fob |
| Cloud Management | ✓ Borealis | ✓ Borealis | ✗ Local only |
| Mobile Credentials | ✓ 700 Connekt | ✓ 700 Connekt | ✗ Not available |
| Keypad PIN Entry | ✗ | ✓ | ✓ |
| Monthly Fees | $199.50/mo | $199.50/mo | $0/mo |
| Year 1 Total | $22,997 | $25,945 | $20,955 |
| Year 2+ Annual | $9,394* | $9,394* | $0 |
| Workstation Required | No (browser) | No (browser) | Yes (included) |
| Remote Mgmt | ✓ Anywhere | ✓ Anywhere | Via ASI 360 gateway |

*Year 2+ Annual = Borealis cloud subscription ($2,394) + Connekt mobile credential renewals ($7,000). V3 has no recurring fees.

All three options retain the existing PXL-500 controllers, wiring, power supply, and enclosures. The primary differences are in the reader technology, credential types, and management platform.