Allied Systems Integrations

PROJECT PROPOSAL

Version 3.0

On-Premise Access Control System Upgrade

Keri NXT + Doors.NET | 10-Door Clubhouse Configuration

PREPARED FOR

Diamond Heights Village Association

c/o PMP Management, LLC

Attn: Melissa Tolerton

115 Red Rock Way, San Francisco, CA 94131

March 18, 2026

## Confidentiality Notice

This document contains proprietary and confidential information belonging to ASI 360 (Allied Systems Integrations). The information provided herein is intended solely for the use of Diamond Heights Village Association and its authorized representatives. Distribution, reproduction, or disclosure of this document or its contents to any third party without the prior written consent of ASI 360 is strictly prohibited.

All pricing, technical specifications, and methodologies described herein are valid for thirty (30) days from the date of this proposal unless otherwise stated.

# Cover Letter

March 18, 2026

Diamond Heights Village Association

c/o PMP Management, LLC

Attn: Melissa Tolerton

115 Red Rock Way

San Francisco, CA 94131

Dear Ms. Tolerton,

Thank you for the opportunity to assess the access control system at Diamond Heights Village. Following our detailed evaluation of your existing Keri Systems PXL-500 infrastructure, we are pleased to present this proposal for a traditional on-premise system upgrade using Keri NXT controllers and Doors.NET software.

This approach provides full local control with no monthly subscription fees — a one-time investment that keeps all system management on-site. The trade-off is that cloud-based remote management and mobile phone credentials are not available with this configuration. Day-to-day operation does not require an internet connection.

This proposal includes a complete needs assessment based on our on-site evaluation, a detailed technical solution design, an itemized investment summary, and our recommended implementation timeline. We have designed this solution to address the specific challenges faced by your community, including aging readers, the need for modern credential management, and enhanced security for common areas.

We look forward to discussing this proposal with you and the Board of Directors. Please do not hesitate to contact us with any questions.

Sincerely,

ASI 360 — Allied Systems Integrations

San Francisco Bay Area

info@asi360.co | (510) 288-0994

# Executive Summary

Diamond Heights Village Association operates a Keri Systems PXL-500-based access control system controlling 10 doors across the residential complex. The system uses legacy NXT/MS-series proximity readers with a PXL-250 Tiger Controller as the head-end. While the core infrastructure remains functional, the readers are aging, the Tiger controller lacks cloud management capability, and the community has no modern credential options.

ASI 360 proposes a traditional on-premise upgrade using Keri NXT reader/keypad kits with Doors.NET software running on a dedicated managed workstation. This approach provides full local control with no monthly subscription fees — a one-time capital investment. The trade-off is that cloud-based remote management and Conekt mobile phone credentials are not available with this configuration; residents use key fobs and/or PIN codes.

Hardware Investment: $14,754.53 (incl. tax)

Services Investment: $6,200.00

Combined Total: $20,954.53

Monthly Recurring Fees: $0.00

Estimated Timeline: 4-5 weeks from signed acceptance

Payment Terms: 50% deposit / 40% on install / 10% on commissioning

# Needs Assessment

Based on our comprehensive assessment of the Diamond Heights Village access control system, we identified the following conditions and risk factors that drive the need for a system upgrade.

## Current System Conditions

- 10-door access control system with 10 proximity readers across residential HOA complex

- 4x Keri PXL-500 controllers (2018-2019 manufacture) in KRE-2 enclosures — functional, good condition

- 1x PXL-250 Tiger Controller serving as head-end — functional but legacy technology, no cloud capability

- 8x MS-5000 series mullion readers — fair condition, significant weathering from outdoor exposure

- 2x NXT-2R/3R mid-size readers — poor condition, severe UV degradation, priority replacement

- KPS-11 power supply with ESD X-1656 transformer — good condition, compatible with upgrade

- 2x Interstate FAS1075 backup batteries (12V 7Ah) — age unknown, on-site testing recommended

- All readers use legacy 26-bit Wiegand NXT/MS proximity technology

- Existing wiring infrastructure (Wiegand runs, power, RS-485 bus) is intact and reusable

## Risk Factors

- Tiger PXL-250 controller has no cloud management — all changes require on-site visits

- Legacy proximity-only readers provide no mobile credential or PIN code capability

- UV-degraded readers (Readers 2 and 3) are at risk of failure

- No audit trail capability — cannot track who accessed what door and when

- Credential management requires physical office visits to issue/revoke fobs

- No temporary or guest credential capability for contractors and visitors

- Pool and common area access lacks granular time-based scheduling

- Competitor quote (Warman Security) is active — 30-day expiration window

- Aging backup batteries may not sustain system during power outages

# Proposed Solution

ASI 360 recommends an on-premise Keri NXT upgrade with Doors.NET software, giving Diamond Heights Village a fully self-contained access control system with no cloud dependency or recurring subscription fees.

## System Components

- 1x Spare PXL-500W Door Controller — Retaining the existing 4x PXL-500 boards; this spare provides immediate redundancy. If any board fails, the spare slots in with zero downtime.

- LAN-520AESP Ethernet Communication Module — Connects the PXL-500 controller network to the building LAN, enabling Doors.NET to communicate with all controllers over standard Ethernet rather than serial.

- 10x Keri NXT-KPK Reader + Keypad Kits (NXT-6RK reader + NXT-RM3 mounting) — Replace all existing MS-5000 and NXT-2R/3R readers. Dual-entry: proximity fob tap and illuminated keypad for PIN codes.

- 200 Conekt Proximity Key Tags (4x CSK-2-50 packs) — Immediate credentialing for all residents. Compatible with existing 26-bit Wiegand format.

- Doors.NET Basic Edition Software (KERI-DNET-BASIC) — Full-featured access control management software with audit trail, event monitoring, door scheduling, reporting, and badge management. Runs locally on the dedicated workstation.

- Keri Access Control Gateway License (SW-PGWM) — Enables secure remote access for ASI 360 support staff to manage the system without on-site visits.

- ASI 360 Keri Hub Workstation (Dell OptiPlex i7/32GB/1TB) — Pre-configured managed workstation dedicated to running Doors.NET. Includes OS, software installation, network configuration, and ASI 360 remote monitoring agent.

- KPS-3 Power Supply (2.8A @ 12VDC) — Additional power supply for the spare controller board.

- 2x Replacement Backup Batteries (12V 7Ah SLA) — Ensures reliable power backup during outages.

## Retained Equipment

- 4x PXL-500 controllers (connected via LAN-520AESP)

- 5x KRE-2 enclosures

- KPS-11 power supply (existing)

- ESD X-1656 transformer

- All existing wiring (Wiegand runs, power, RS-485 bus)

## What This Means for Residents

With the NXT on-premise approach, residents access the building using a key fob tap or a personal PIN code — or both. There is no mobile app or cloud account to set up. Property management issues and revokes credentials directly from the on-site workstation. The system operates independently of the internet, so access control continues to function even during network outages.

The ASI 360 gateway license allows our team to provide remote support, firmware updates, and troubleshooting via a secure VPN connection — meaning most service requests can be handled without scheduling an on-site visit.

# Key Benefits

- No monthly subscription fees — one-time investment with zero recurring costs

- Full local control — no internet dependency for day-to-day access control operation

- NXT reader + keypad combo — residents use fob tap AND/OR PIN code entry

- Doors.NET software with full audit trail, door scheduling, reporting, and event monitoring

- ASI 360 managed workstation with remote gateway license for ongoing support access

- Scalable — add doors and controllers as campus expands, no per-door subscription

- 200 key fobs (4 × 50-packs) for immediate resident credentialing on Day 1

- Spare PXL-500W controller for redundancy — zero downtime if a board fails

- Complete audit trail for compliance and liability protection

- Pool safety — controlled access prevents unauthorized entry (liability reduction)

- Package theft prevention — secured mail/package room access

- Contractor access: temporary fobs or PINs with defined schedules

- Instant move-out revocation — disable fobs and PINs from the workstation

# Investment Summary

## Hardware & Equipment

| # | Item (SKU) | Description | Qty | Unit Price | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | PXL-500W | Keri PXL-500W Door Controller (spare, retaining existing 4 boards) | 1 | $1,150.00 | $1,150.00 |
| 2 | LAN-520AESP | Ethernet Network Communication Module | 1 | $385.00 | $385.00 |
| 3 | NXT-KPK | Keri NXT Reader + Keypad Kit (NXT-6RK + NXT-RM3) | 10 | $785.00 | $7,850.00 |
| 4 | CSK-2-50 | Conekt Proximity Key Tags (50-pack) | 4 | $520.00 | $2,080.00 |
| 5 | KERI-DNET-BASIC | Doors.NET Basic Edition Software License | 1 | $495.00 | $495.00 |
| 6 | SW-PGWM | Keri Systems Access Control Gateway License | 1 | $750.00 | $750.00 |
| 7 | DELL-OPT7050 | ASI 360 Keri Hub — Managed Workstation (Dell OptiPlex i7/32GB/1TB) | 1 | $625.00 | $625.00 |
| 8 | KPS-3 | Power Supply 2.8A @ 12VDC | 1 | $175.00 | $175.00 |
| 9 | 12V-7AH-SLA | Backup Battery (12V 7Ah SLA) | 2 | $36.50 | $73.00 |
|  |  | Hardware Subtotal |  |  | $13,583.00 |
|  |  | CA Sales Tax (8.625%) |  |  | $1,171.53 |
|  |  | Hardware Total |  |  | $14,754.53 |

## Services & Installation

| # | Item | Description | Qty | Unit Price | Amount |
| --- | --- | --- | --- | --- | --- |
| 1 | INSTALL-READER | Reader removal, mounting, wiring, termination | 10 | $185.00 | $1,850.00 |
| 2 | INSTALL-CTRL | Controller board inspection, firmware check, LAN module install | 1 | $650.00 | $650.00 |
| 3 | WORKSTATION | Workstation setup, Doors.NET install, network config, gateway | 1 | $950.00 | $950.00 |
| 4 | PROGRAM | System programming, credential enrollment, door scheduling, testing | 1 | $1,200.00 | $1,200.00 |
| 5 | TRAINING | Property management staff training (2 sessions) | 1 | $500.00 | $500.00 |
| 6 | PM | Project management, coordination, documentation | 1 | $800.00 | $800.00 |
| 7 | DISPOSAL | Legacy Tiger controller + old reader disposal | 1 | $250.00 | $250.00 |
|  |  | Services Total |  |  | $6,200.00 |

## Combined Investment

Hardware Total (incl. tax): $14,754.53

Services Total: $6,200.00

Combined Project Total: $20,954.53

Monthly Recurring Fees: $0.00

# Terms & Conditions

## Payment Terms

- 50% deposit upon signed acceptance to initiate equipment procurement

- 40% upon completion of hardware installation

- 10% upon system commissioning, testing, and client sign-off

## Warranty

- All labor warranted for one (1) year from date of commissioning

- Manufacturer hardware warranties apply per Keri Systems and Farpointe standard terms

## Scope Exclusions

- Electrical work beyond low-voltage access control wiring

- Door hardware modifications, lock replacements, or gate operator repairs

- Network infrastructure (Ethernet drops, switches, routers, ISP coordination)

- Painting, patching, or cosmetic repairs following reader replacement

- Wiring repairs discovered during installation will be quoted separately on a T&M basis

## Timeline

- Equipment lead time: 2-3 weeks from deposit

- Installation: 2-3 business days

- Commissioning and training: 1 business day

- Estimated project completion: 4-5 weeks from signed acceptance

## Validity

This proposal is valid for thirty (30) days from the date shown on the cover page. Pricing is subject to change after the validity period due to manufacturer price adjustments and equipment availability.

# Acceptance

By signing below, the authorized representative of Diamond Heights Village Association accepts this proposal and authorizes ASI 360 to proceed with the project as described herein.

________________________________________          ________________

Authorized Signature                                                        Date

________________________________________

Printed Name & Title

ASI 360 — Allied Systems Integrations

San Francisco Bay Area | info@asi360.co | (510) 288-0994

# Comparison at a Glance

The following table summarizes all three proposal options side by side to assist the Board of Directors in evaluating the best fit for Diamond Heights Village.

| Feature | V1 Borealis Mobile | V2 Hybrid Keypad | V3 NXT Standard |
| --- | --- | --- | --- |
| Entry Methods | Fob + Mobile | PIN + Fob + Mobile | PIN + Fob |
| Cloud Management | ✓ Borealis | ✓ Borealis | ✗ Local only |
| Mobile Credentials | ✓ 700 Connekt | ✓ 700 Connekt | ✗ Not available |
| Keypad PIN Entry | ✗ | ✓ | ✓ |
| Monthly Fees | $199.50/mo | $199.50/mo | $0/mo |
| Year 1 Total | $22,997 | $25,945 | $20,955 |
| Year 2+ Annual | $9,394* | $9,394* | $0 |
| Workstation Required | No (browser) | No (browser) | Yes (included) |
| Remote Mgmt | ✓ Anywhere | ✓ Anywhere | Via ASI 360 gateway |

*Year 2+ Annual = Borealis cloud subscription ($2,394) + Connekt mobile credential renewals ($7,000). V3 has no recurring fees.

All three options retain the existing PXL-500 controllers, wiring, power supply, and enclosures. The primary differences are in the reader technology, credential types, and management platform.